Field fieldwealth.ai SALESFORCE INTEGRATION Middle-Path Roadmap Native FA/Team, Brief and Ask Field inside Salesforce, with the full Field dashboard suite embedded. Packaged for multiple asset manager clients through AppExchange. DATE October 7, 2026 STATUS Draft for discussion · estimates, not commitments POWERED BY Field Confidential · For internal use only.

# 1. Summary

Field will ship a managed Salesforce package that brings three high-use screens into Salesforce natively, on desktop and mobile: the FA/Team panel, the Brief and Ask Field. The full dashboard suite stays in the Field portal and is embedded in a Field tab with single sign-on. Field remains the system of record; Salesforce holds only CRD references, configuration and optional Tasks.

This approach delivers most of the native experience at roughly 60% of the cost of rebuilding the full suite, and lets usage data decide what moves native next.

| Item | Plan |
| --- | --- |
| Approach | Native for FA/Team, Brief, Ask Field; full suite embedded |
| Distribution | Managed package on AppExchange for multiple asset manager clients |
| Primary platform | Sales Cloud, plus the Salesforce mobile app |
| Timeline | Embedded suite demo-able at week 10; production pilot at week 24; AppExchange listing around week 32 |
| Build team | About 5 FTE equivalent during build |
| Run cost | About 1–1.5 engineers after launch |

## Assumptions

- Asset manager clients share their Salesforce data with Field.

- CRD matching to industry data packs, and team definitions (client teams or FINTRX), are already planned in Field and are not part of this estimate.

- Most clients run Sales Cloud. Financial Services Cloud is supported but not optimized for in phase 1.

- Mobile is a slimmed-down experience limited to the Brief, Ask Field and the FA/Team page.

# 2. Scope

| Area | In scope | Delivery |
| --- | --- | --- |
| FA/Team panel | Field summary, top signals, recommended action, key metrics, “Open in Field” link on Contact and Account pages | Native, desktop and mobile |
| Brief | Role-aware Brief (wholesaler or manager) on the Home page and a mobile page | Native, desktop and mobile |
| Ask Field | Chat panel in the utility bar and on record pages; mobile quick action; aware of the FA/Team on screen | Native, desktop and mobile |
| Dashboard suite | Territory Analytics, leadership dashboards, Briefs & Reviews, Data Packs and the rest of the portal | Embedded Field tab with SSO and deep links |
| Admin setup | CRD field mapping, team source, Task write-back, connection test | Native setup page |
| Write-back | Optional Salesforce Tasks created from signals | Native, off unless the admin enables it |

## Out of scope

- Native rebuilds of the full dashboard suite.

- Offline mode in the Salesforce mobile app.

- Copying Field data into Salesforce custom objects beyond configuration and Tasks.

- CRD matching and team modeling (covered by existing Field plans).

# 3. Roadmap at a glance

| Phase | Weeks | Outcome |
| --- | --- | --- |
| 0 · Setup and architecture | 1–4 | Architecture, service contract and designs signed off |
| 1 · Foundation and embedded suite | 5–10 | Package installs; full suite opens in Salesforce with SSO |
| 2 · Native FA/Team panel | 9–15 | Same signals in Salesforce as in Field, desktop and phone |
| 3 · Brief and Ask Field | 13–19 | All three native screens complete |
| 4 · Hardening and pilot | 18–24 | Pilot clients using it daily; security package ready |
| 5 · AppExchange review and launch | 24–32 | Listed on AppExchange; repeatable 1–2 day install |

Timeline by month (about 4 weeks each)

| Phase | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0 · Setup |  |  |  |  |  |  |  |  |
| 1 · Foundation |  |  |  |  |  |  |  |  |
| 2 · FA/Team panel |  |  |  |  |  |  |  |  |
| 3 · Brief + Ask Field |  |  |  |  |  |  |  |  |
| 4 · Hardening + pilot |  |  |  |  |  |  |  |  |
| 5 · Review + launch |  |  |  |  |  |  |  |  |

# 4. Phase detail

## Phase 0 · Setup and architecture

Weeks 1–4

- Join the Salesforce partner program; register the package namespace and developer orgs.

- Sign-in for the embedded tab: single sign-on into the portal, with Salesforce as the identity provider or each client’s existing SSO.

- Sign-in for native screens: an OAuth connection from each client’s Salesforce org to Field, with Salesforce users linked to Field users by email or SSO ID.

- Define the service contract Field exposes: Brief, FA/Team summary, signals, Ask Field, setup and health check.

- Set data rules: Field is the system of record; Salesforce stores CRD references, configuration and optional Tasks only.

- Design compact desktop and mobile layouts for the three native screens.

DONE WHEN Architecture signed off, service contract agreed, designs approved.

## Phase 1 · Foundation and embedded suite

Weeks 5–10

- Package skeleton: release pipeline, permission sets for reps and managers, and a “Field” app in Salesforce.

- Field-side: keys per client, service endpoints, rate limits and logging.

- Embedded suite: a Field tab that opens the portal already signed in, plus deep links that land on a specific FA/Team page.

- Admin setup page: CRD field mapping, team source (client or FINTRX), Task write-back on or off, connection test.

DONE WHEN A pilot org installs the package, connects, opens the full suite on the Field tab and clicks from an FA through to the matching Field page.

## Phase 2 · Native FA/Team panel

Weeks 9–15

- Record-page panel for Contacts (FAs) and Accounts or teams: Field summary, top signals, recommended action, key metrics and “Open in Field”.

- Mobile layout with stacked cards and large tap targets.

- States for no CRD match, no data and errors.

- Optional: create a Salesforce Task from a signal.

DONE WHEN A rep on an FA page, on desktop or phone, sees the same signals as the Field FA/Team page.

## Phase 3 · Brief and Ask Field

Weeks 13–19

- Brief: Home page component and mobile page, role-aware (wholesaler or manager), using the same content as the email brief.

- Ask Field: chat panel in the utility bar and on record pages, plus a mobile quick action.

- Ask Field knows the FA/Team on screen, so “What should I talk to Smith Group about?” works without naming the team.

- Answers arrive progressively through Salesforce, or stream directly from Field if that option is chosen.

- Usage tracking for every native screen and the embedded tab.

DONE WHEN All three native screens work on desktop and mobile in a test org.

## Phase 4 · Hardening and pilot

Weeks 18–24

- Test across org setups: profiles, sharing rules and custom Contact fields.

- Device testing on iOS and Android in the Salesforce mobile app.

- Performance target: FA/Team panel loads in under 2 seconds.

- Security preparation: code scan, penetration test of Field’s servers (in scope for the review) and security documentation.

- Pilot with one or two asset managers, sandbox first, then production; collect feedback and fix issues.

DONE WHEN Pilot clients use it daily and the security package is ready to submit.

## Phase 5 · AppExchange review and launch

Weeks 24–32

- Submit for security review; plan for one round of fixes.

- Listing: description, screenshots, demo org and pricing model.

- Onboarding kit: install guide, admin setup checklist and rep quick-start.

DONE WHEN Listed on AppExchange with a repeatable install of about 1–2 days per client.

## Ongoing, after launch

- Regression testing for each of Salesforce’s three releases a year.

- Client onboarding, support and package updates.

- Move further screens native when usage data shows which embedded screens reps open most.

# 5. Team and staffing

| Role | Allocation | When |
| --- | --- | --- |
| Salesforce lead / architect | 1.0 | Phases 0–5 |
| Salesforce developers | 2.0 | Phases 1–5 |
| Field backend developer | 1.0 | Mainly phases 1–3 |
| QA | 0.5 | Phases 2–5 |
| Designer | 0.5 | Phases 0–3 |
| After launch | 1–1.5 engineers | Ongoing |

## Milestones

| Week | Milestone |
| --- | --- |
| 10 | Embedded suite live in a pilot org; demo-able to clients |
| 19 | All native screens complete |
| 24 | Production pilot |
| ~32 | AppExchange listing |

# 6. Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| AppExchange security review | Longest lead item; first submissions often fail | Pen-test Field’s servers early; scan code every sprint; budget a fix round |
| Different setups at each client | Custom fields, profiles and sharing rules break assumptions | Admin setup page; test against several org shapes; budget time per install |
| Mobile app limits | Chart libraries and offline behavior are restricted | Keep mobile screens simple; link to Field for deep analysis |
| Ask Field response delivery | Salesforce server calls cannot stream answers | Decide early between progressive delivery and direct streaming from Field |
| Partner program terms | Agreement and revenue share affect pricing | Confirm current terms with a Salesforce partner manager in phase 0 |

## Decisions to make early

| Decision | Options | Needed by |
| --- | --- | --- |
| Ask Field delivery | Through Salesforce servers, or directly from Field | Week 4 |
| Task write-back default | On by default, or off until the client admin enables it | Week 8 |
| Pricing | Per user, per org, or bundled into existing data pack tiers | Week 20 |
| Pilot clients | Which one or two asset managers, and whether their Salesforce setup is typical | Week 12 |